## Gantt Chart
FINE SCANDINAVIA SUPPLY CHAIN CAPSTONE PROJECT | [6 empty] | GROUP | [5 empty] | PANDA
PROJECT TITLE |  | FINE SCANDANAVIA SUPPLY CHAIN PROJECT |  |  |  |  | COMPANY NAME | [6 empty] | FINE SCANDANAVIA
PROJECT MANAGER |  | MR. Le Thanh Hai |  |  |  |  | DATE | [6 empty] | 11st Jul 2025
Criteria | TASK TITLE | TASK OWNER | START DATE | DUE DATE | DURATION | STATUS | Week 1 | [14 empty] | WEEK 3 | [6 empty] | WEEK 4
[7 empty] | M | T | W | T | F | S |  |  |  |  | S |  |  |  |  | M | T | W | T | F | S | S
[7 empty] | 30th | 1st | 2nd | 3rd | 4th | 5th | 13th | 14th | 15th | 16th | 17th | 18th | 19th | 20th | 6th
Main | Company analysis | All members
Sub | Vision & Mission | Yen | 2025-07-11 | 2025-07-13 | 2 | Done | bar: 4th to 16th; 6th
Sub | Business model | Ai | 2025-07-11 | 2025-07-13 | 2 | Done | bar: 4th to 6th
Sub | Operational Structure | Binh | 2025-07-11 | 2025-07-13 | 2 | Done | bar: 4th to 6th
Sub | Supply Chain model | Tuan Anh | 2025-07-11 | 2025-07-13 | 2 | Done | bar: 4th to 16th; 18th to 6th
Sub | Risk, Challenge & Solution | All members | 2025-07-11 | 2025-07-13 | 2 | Done | bar: 4th to 6th
Sub | Others | All members | 2025-07-11 | 2025-07-13 | 2 | Done | bar: 4th to 6th
Main | Demand planning
Sub | Identify demand sources | All members | 2025-07-11 | 2025-07-12 | 1 | Done | bar: 13th to 16th
Sub Lv2 | Customer segmentation | All members | 2025-07-11 | 2025-07-12 | 1 | Done | bar: 13th to 16th
Sub Lv3 | Forecasting sources from manufacturers, distributors, customers, wholesellers | All members | 2025-07-11 | 2025-07-12 | 1 | Done | bar: 13th to 20th
Sub Lv4 | Sources of Demand planning | All members | 2025-07-11 | 2025-07-12 | 1 | Done | bar: 13th to 16th
Main | Project demand
3.1 | Identidy product quantity | All members | 2025-07-25 |  | 0 | Done
3.2 | KPIs | All members | 2025-07-25 |  | 0 | Done
3.2.1 | Monitoring | All members | 2025-07-25 |  | 0 | Done
3.2.2 | Forecasts | All members | 2025-07-25 |  | 0 | Done
3.3 | Project Updates | All members | 2025-07-25 |  | 0 | Done
3.3.1 | Chart Updates | All members | 2025-07-25 |  | 0 | Done
Main | Supply planning structure
Sub | MPS calulation research 1 | Binh | 2025-07-26 |  | 0 | Done
Sub | MPS calulation research 2 | Ai | 2025-07-26 |  | 0 | Done
Sub | MPS calulation research 3 | Yen | 2025-07-26 |  | 0 | Done
Sub | MPS | Binh, Yen | 2025-07-26 |  | 0 | Done
Main | Purchasing strategy
Sub | BOM | Binh, Ai, Tuan Anh | 2025-07-26 |  | 0 | Done
Sub | Annual demand for all components | Ai, Binh | 2025-07-26 |  | 0 | Done
Sub | Evaluate and clasify suppliers | Binh, Ai, Tuan Anh | 2025-07-26 |  | 0 | Done
Sub | Build purchasing strategy | Bình | 2025-07-26 |  | 0 | Done
Main | Remaining
Sub | Quality Management | Ai | 2025-08-01 |  | 0 | Done
Sub | Sustainability & EPR Compliance | Binh, Yen | 2025-08-01 |  | 0 | Done
Sub | Information‑System Specification | Tuan Anh | 2025-08-01 |  | 0 | Done
Sub | Logistics Network Design | Ai | 2025-08-08 |  | 0 | Done
Main | Report + Presentation
Sub | Introduction + Information strategy + Conclusion | Yen | 2025-08-13 | 2025-08-15 | 0 | Done
Sub | Demand Planning + Logistics Network Design | Ai | 2025-08-13 | 2025-08-15 | 0 | Done
Sub | Supply Planning + Quality Management Plan | Tuan Anh | 2025-08-13 | 2025-08-15 | 0 | Done
Sub | Purchasing strategy + Sustainability & EPR Compliance | Binh | 2025-08-13 | 2025-08-15 | 0 | Done